## Sheet1
OWNER_NAME | WORKBOOK_NAME | SITE_NAME | DB Connection Types | Rationalization Disposition Decision by BU | CAPG Complexity Rating | Internal/External Capacity | Delivery Ownership | Target Platform | Current Data Pathway | DE Support Needed | Conversion Status | Technical Sign Off | Business Sign Off | Notes | Resource Already allocated? Yes or No | Dashboard Priority | Dashboard Complexity
Lizarraga Andere, Jose Mario | LPC DBB Report | Industrial Segment | excel-direct, redshift, hyper | Keep | High | External | CAPG | Power BI | Tableau Prep |  | Not Started
Lizarraga Andere, Jose Mario | CLS S&D Summary | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Smith, Chris | Resource Capacity and Forecast | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Smith, Chris | Projects Linked to SFDC | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Lizarraga Andere, Jose Mario | Mfg Source Books/Billings Report | Industrial Segment | excel-direct, redshift, textscan, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Lizarraga Andere, Jose Mario | CLS Currency | Industrial Segment | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Hernandez, Brigette Jane M | Wave Dashboard V2 | Universal | excel-direct, databricks | Keep | N/A | External | CAPG | Power BI |  |  | Not Started |  | David Debeljak/Crissia Tolentino/Almira Jane Lizardo
Zhang, Jacky | DDN Global Supplier Quality Management Dashboard | Industrial Segment | excel-direct, hyper | Keep | High | External | CAPG | Power BI | Tableau Prep |  | Not Started
Mignon, Matthieu | DQIP_Suivi_AWS | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Katruk, Tanya | Scrap Dashboard Prior Month | Transportation Segment | redshift | Keep | High | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Scrap Dashboard | Transportation Segment | redshift | Keep | High | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Plant Recovery | Transportation Segment | redshift | Keep | High | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Standard Costs | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Published Consensus Forecast 2026 FM11 | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Plant Recovery History | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | QC Hold | Transportation Segment | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Labor Efficiency Prior Fiscal Month | Transportation Segment | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Labor Efficiency | Transportation Segment | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Katruk, Tanya | Cost To Serve | Transportation Segment | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Aguilar, Evian Drew A | PM LT Dashboard | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Shrivastava, Stuti | Freight Spend Dashboard | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Oulayachi, Mohcine | INDG Daily inventory Snapshot v2.5(Report) | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Oulayachi, Mohcine | Inventory Daily movment IND | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Rehounek, Tomas | Industrial Inventory Dashboard | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Oulayachi, Mohcine | GIT 2.3 (Dashboard) | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Witaszek-Pawelczuk, Patrycja | Workload | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Witaszek-Pawelczuk, Patrycja | Sales vs Purch InfoRec MOQ | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Purchasing MOQ Analysis | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Exceptiom message | Industrial Segment | redshift, hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Daily Inventory Snapshot DB | Industrial Segment | textscan, hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Yumul, Mark Dale F | Control Tower Dashboard | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Yumul, Mark Dale F | Backlog_PRS_450 Report | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Backlog Dynamics | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | IBP WorkCenters - Total Adjusted Capacity Routings | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | IBP WorkCenters - Demonstrated Output Routings | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | IBP Part Numbers - Historical Demand Routings | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | IBP Part Numbers - Backlog Routings | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Witaszek-Pawelczuk, Patrycja | TEOA Metrics | Industrial Segment | redshift, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | PDR - Executive | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Inventory weekly snapshot | Industrial Segment | excel-direct, onedrivesharepoint, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Industrial RCCP 1099 | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Witaszek-Pawelczuk, Patrycja | IAE Portfolio Health | Industrial Segment | redshift, onedrivesharepoint, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Customer Centric Dashboard | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Jezek, Martin | BACKLOG | Industrial Segment | 0 | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | PDROperationaldetail2_3 | Industrial Segment | excel-direct, textscan, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Inventory Daily Dashboard | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Industrial Delivery Reliability | Industrial Segment | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Industrial Backlog & Past Dues Dashboard | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Altamirano, Ivan Alberto | Currency - Week over Week | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Rullo, Daniel J | ICT Negative Margin Dashboard | Transportation Segment | excel-direct, hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Woeber, Andreas | TEBIT_AW_2025_06 | Transportation Segment | 0 | Keep | Low | External | CAPG | Power BI | SQL Editor |  | Not Started |  |  | will review with Owner and update accordingly, if owner is not taking any action, it will be given to external
Woeber, Andreas | Sustaining Eng. Task Tracker | Transportation Segment | msaccess | Keep | Low | External | CAPG | Power BI | Other |  | Not Started |  |  | will review with Owner and update accordingly, if owner is not taking any action, it will be given to external
Kundagol, Priyanka | PM - MOQ validation dashboard | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI | Alteryx |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Rullo, Daniel J | Book Pricing GPMS Format | Transportation Segment | redshift, oracle | Keep | Low | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Kundagol, Priyanka | ICT Top Offenders | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI | Alteryx |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Khatun, Sumaiya | ICT SMA CODE Dashboard | Transportation Segment | redshift | Keep | Low | External | CAPG | Power BI | Alteryx |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Khatun, Sumaiya | Global Standard Cost Dashboard ICT | Transportation Segment | redshift | Keep | Low | External | CAPG |  |  |  | Not Started |  |  | Not sure what is the source of this dashbaord and its not avaialable in our list
Boumedyane, Yassine | DPIM Report | Transportation Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started |  |  | Not listed in our list, please confirm the source
Rullo, Daniel J | Commodity Review | Transportation Segment | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Rullo, Daniel J | Commodity Increase Tracker | Transportation Segment | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Rullo, Daniel J | Price Erosion Overview FY26 | Transportation Segment | oracle | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Kundagol, Priyanka | Non-ICT_PN_Analysis | Transportation Segment | redshift | Keep | Medium | External | CAPG | Power BI | Alteryx |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Rullo, Daniel J | Non-ICT Negative Margin Dashboard | Transportation Segment | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Elmoutaraji, Hamza | Logistics Follow-up | Transportation Segment | 0 | Keep | Medium | External | CAPG | Power BI | SQL Editor |  | Not Started |  |  | Need to check One Current data path way with the owners, will check on Monday and add the details here
Boyineni, Jael | DoH | Industrial Segment | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep | No | Not Started | Boyineni, Jael | Fernandez, Ma. Veronica | Good to have same resource assigned to work on MED Inventory Dashboard, MED Inventory Summary by Vendor & DoH- As These 3 reports are connected |  | 5 | Medium
D'Anna, Alfonso | Prod_Metric_rev1 | Transportation Segment | saphana | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Patel, Divykumar | Probe Heatmap and Histogram | Transportation Segment | excel-direct | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | [Sensors specific]
Using SAP MES - Manufacturing Execution --- being maintained by CapGemini - Sensors specific tools - FSO S72 (California) & S81 (Germany) also uses the same system.
Need help from DIA to migrate due to lack of bandwidth on their end
Will check with his managers to check all the dashboards needed to be migrated
D'Anna, Alfonso | Ni1000_temp | Transportation Segment | saphana, onedrive | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | [Sensors specific] Dashboard creator left TE (Denisa Jurcan). Need to change Owner for Tableau folder. Need business continuity. Opportunity for HC DIA or additional workload.
Sampelly, Prudhvi Koushik Rao | MLPT Yield | Transportation Segment | excel-direct, saphana | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | [Sensors specific]
Using SAP MES - Manufacturing Execution --- being maintained by CapGemini - Sensors specific tools - FSO S72 (California) & S81 (Germany) also uses the same system.
Need help from DIA to migrate due to lack of bandwidth on their end
Will check with his managers to check all the dashboards needed to be migrated
Sampelly, Prudhvi Koushik Rao | kpi visualizations for display | Transportation Segment | saphana | Keep | Medium | External | CAPG | Power BI |  |  | Not Started |  |  | [Sensors specific]
Using SAP MES - Manufacturing Execution --- being maintained by CapGemini - Sensors specific tools - FSO S72 (California) & S81 (Germany) also uses the same system.
Need help from DIA to migrate due to lack of bandwidth on their end
Will check with his managers to check all the dashboards needed to be migrated
Nguyen, Thao | TS scope 3 dashboard | Transportation Segment | excel-direct, hyper | Keep | High | External | CAPG | Power BI | Tableau Prep |  | Not Started
Sales, Paul Lawrence Z | CMSE-CEFS Certifications | Universal | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Sales, Paul Lawrence Z | Action Items Status | Universal | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep | No | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Sales, Paul Lawrence Z | Self Assessment | Universal | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep | No | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Sales, Paul Lawrence Z | SAFE Schedule Audit Dashboard | Universal | onedrivesharepoint, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Sales, Paul Lawrence Z | Self Assessment Progress | Universal | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep | No | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Guerrero, Ma. Criselda R | Safety Alert Dashboard | Universal | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Guerrero, Ma. Criselda R | SAFE Scoring Status | Universal | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Shetty, Ashwitta R | Channel Pricing dashboards adhoc | Distribution Channel Business | sqlserver | Keep | High | External | CAPG | Power BI |  |  | In Progress
Shetty, Ashwitta R | Channel Pricing dashboards adhoc tereg-mcp | Distribution Channel Business | sqlserver | Keep | High | External | CAPG | Power BI |  |  | In Progress
Shetty, Ashwitta R | Channel Pricing dashboards MCP adhoc | Distribution Channel Business | sqlserver | Keep | High | External | CAPG | Power BI |  |  | In Progress
Shetty, Ashwitta R | Channel Pricing dashboards sales | Distribution Channel Business | sqlserver | Keep | High | External | CAPG | Power BI |  |  | In Progress
Shetty, Ashwitta R | Channel Pricing dashboards adhoc tereg | Distribution Channel Business | sqlserver | Keep | Medium | External | CAPG | Power BI |  |  | In Progress
Shetty, Ashwitta R | Competitor Comparison Analysis Dashboard with cbc | Distribution Channel Business | sqlserver | Keep | Medium | External | CAPG | Power BI |  |  | Dashboard Complete
Sengupta, Prasanjit | SMA Time Period Waterfall - Phase I-FY25 | Corporate Marketing | excel-direct, hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Sengupta, Prasanjit | SMA Time Period Waterfall - Phase I FY24 | Corporate Marketing | excel-direct, hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Maharana, Sushweta | Ecommerce Performance Dashboard | Corporate Marketing | excel-direct, redshift | Keep | High | External | CAPG | Power BI |  |  | Not Started
Maharana, Sushweta | SMA Time Period Waterfall - Phase I | Corporate Marketing | excel-direct, hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Umarani, Umesh Ramesh | Won-Lost Business | Corporate Marketing | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Umarani, Umesh Ramesh | Ecommerce_Sales_Dashboard | Corporate Marketing | redshift | Keep | Low | External | CAPG | Power BI |  |  | Not Started
S K, Prakruthi | SLA_Dashboard_v2 | Corporate Marketing | textscan | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Narah, Bhairab | SMA_Campaign_Dashboard - FY24 Year End | Corporate Marketing | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Umarani, Umesh Ramesh | Customer_360_Prototype_COE | Corporate Marketing | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Narah, Bhairab | SMA_Campaign_Dashboard - FY25 Year End | Corporate Marketing | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Maharana, Sushweta | SMA Performance Dashboards - Monthly(old format) | Corporate Marketing | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
S K, Prakruthi | SMA Performance Dashboards - Weekly Updates | Corporate Marketing | excel-direct, textscan | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Maharana, Sushweta | SMA_Campaign_Dashboard | Corporate Marketing | excel-direct, hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Umarani, Umesh Ramesh | Customer _Health_Prototype_IS | Corporate Marketing | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Hobin, Keith | NPS_Dashboard | Universal | databricks | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Umarani, Umesh Ramesh | Sales Insights - Account & Contact Activity Dashboard | Corporate Marketing | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Singh, Abhishek | NPS Contact Data Quality | Corporate Marketing | redshift, databricks | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Sales, Paul Lawrence Z | EHS Raw Data Download | Universal | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep | No | Not Started |  |  | Dependent on Benchmark L0/L1/L2 ingestion | Yes
Sales, Paul Lawrence Z | EHS Passport Training Tracker | Universal | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Szmyd, Karolina | Procurement Data Overview + CM | Global Corporate (Finance/Audit/Legal) | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Kedia, Ahamad S | Talent Scorecard | Human Resources | 0 | Keep | High | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | Talent and Succession Planning 2.0 | Human Resources | redshift | Keep | High | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | HR DASHBOARD | Human Resources | redshift | Keep | High | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | US Candidate Reporting | Human Resources | redshift | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | TR - Core HR Data | Human Resources | redshift | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | GTA SOURCING | Human Resources | redshift | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | concern_line | Human Resources | redshift | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | Market Data | Human Resources | onedrivesharepoint | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Alluri, Vijay | Ireland Clock Data Audit | Human Resources | excel-direct, redshift | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Granados, Aydee Mariana | HRLT SCORECARD | Human Resources | excel-direct | Keep | Low | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | Timely Terminations Dashboard_BOD | Human Resources | 0 | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | Skills Dashboard | Human Resources | 0 | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | CEO Pay Ratio | Human Resources | 0 | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | FY26 HRBPS | Human Resources | textscan | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | Navigate Adoption Dashboard | Human Resources | redshift, hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | YEAR-END RATINGS DASHBOARD | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | Timely Terminations Dashboard | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | OMBUDSMAN HEADCOUNT | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | Internal Mobility Dashboard | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | GTA INSIGHT | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | FY25 YE AUDIT | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | EMEA Works Council Dashboard | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | COMP FLOW | Human Resources | redshift | Keep | Medium | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | GTA 3 (Renamed from GTA 2) | Human Resources | 0 | Keep | N/A | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Lanza, Mariano | FY26 RATINGS DASHBOARD | Human Resources | 0 | Keep | N/A | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Kedia, Ahamad S | FY26 YE REVIEW (Changed from FY25 YE Review) | Human Resources | redshift | Keep | N/A | External | CAPG | Power BI | Other | Yes | Not Started | Vijay Alluri | Mariano Lanza
Delpippo, Anne | Qualité | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Delpippo, Anne | Tier | Industrial Segment | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Bagaporo, Dennis M | CBAM Report | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started |  |  |  | Yes
Chowdoju, Naveen Kumar | EDGE Dashboard test | Corporate Strategy | redshift, hyper, postgres, mysql | Keep | High | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | ION Hub Projection Dashboard | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | Summary Table | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | STS Dashboard ¦ Planner View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | STS Dashboard ¦ Executive View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | STR, STS, OTD, STLT and PDR Dashboard | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | STR Dashboard ¦ Planner View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | STR Dashboard ¦ Executive View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | Ship-To Lead Time Dashboard | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | PDR Dashboard ¦ Planner View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | On-Time Delivery Dashboard | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | Information Page ¦ Planner View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | Information Page ¦ Executive View | Global Supply Chain | hyper | Keep | High | External | CAPG | Power BI |  |  | Not Started
Suresh, Priyanka | P44 GR | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Suresh, Priyanka | P44 data | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Govindaraj, Vijay Castro | Warehouse Heatmap_KC2_draft | Global Supply Chain | excel-direct | Keep | Low | External | CAPG | Power BI |  |  | Not Started
R, Rajaram | Quality CPS Dashboard | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
R, Rajaram | Mode Mix Analysis FAP | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | LOB Home | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started |  |  |  | Yes
Corpuz, Jason Dion A | Inventory Aging Hybrid - WoW perfomance | Global Supply Chain | redshift | Keep | Low | External | CAPG | Power BI |  |  | Not Started
R, Rajaram | GLOG Official Reporting_Quality | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Govindaraj, Vijay Castro | Global Footprint Dashboard | Global Supply Chain | excel-direct | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Freight Weight Optimisation | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard_Overview | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard_Invoice Onhold | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard_Invoice Not Received | Global Supply Chain | hyper | Keep | Low | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard_Credit Note | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard_automatch | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Payment Blocks Dashboard | Global Supply Chain | excel-direct | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | FAP Non Compliance Tracker | Global Supply Chain | 0 | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | DCMS Non-Compliance Scorecard | Global Supply Chain | sqlserver | Keep | Low | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ION HUB Inventory Trend : Velocity & Coverage | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | Rolling 12 Incoterms Dashboard | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ION Hub Inventory Trend Values Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Transportation Transit Time Performance Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Suresh, Priyanka | THDC - Booking Vs FFW Pick up Tracker | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | Status 7 Lags (Aging of Shipments Awaiting Departure) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | Status 5 Lags (Aging of Shipments Awaiting for Pick-up) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | Schedule Attainment New Version | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Quality Holdings Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | PDR Dashboard ¦ Executive View | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (SEN) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (PTS) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (MED) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (ION HUB) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (IND) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (ICT) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (ENG) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (DDN) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (CLS) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (AUT) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (ASG) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Line of Balance (ADM) | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | GLOG COPQ Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | FAP - KPI Dashboard | Global Supply Chain | 0 | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | ETA Status Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | Corporate SC Scorecard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
R, Rajaram | CO2 Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_IND2 | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_IND | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_ICT | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_GATD | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_DND | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_AUT2 | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_AUT | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | ClearToBuild Dashboard_ADM | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | BBS Dashboard | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI | Tableau Prep |  | Not Started
Baguio, Christian Jhon Y | Air Sea Ratio Analysis | Global Supply Chain | hyper | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Baguio, Christian Jhon Y | Air Parcel Optimization Dashboard | Global Supply Chain | redshift | Keep | Medium | External | CAPG | Power BI |  |  | Not Started
Corpuz, Jason Dion A | Executive Dashboard - Enhance version | Global Supply Chain | 0 | Keep | N/A | External | CAPG | Power BI |  |  | Not Started